## Slide 1: SOLARNET DISSEMINATION AND COMMUNICATION PLAN (Outreach Plan)

## Slide 2
Main principles
Coordination of SOLARNET partners individual efforts on public outreach.
Promotion of joint actions specifically designed to enhance the visibility of the project at international level.
Objectives
To make solar physics research more attractive and more comprehensible for a target audience
To achieve visibility for the project and its findings across Europe and worldwide, both inside and outside the scientific community
To promote the awareness of science
To encourage talented students and scientists to join the partner institutes and enterprises
To generate industrial interest for the developed products or services.
Target audiences
Scientific community
Industry
Policy makers and funding agencies of the participants countries
Media
General public
I M P O R T A N T !
The plan should involve all consortium partners.
Actions should be planned and implemented as a continuous process during all the project lifetime, not a one-time effort.
Each target audience requires different messages, means and languages.
All materials should clearly include the SOLARNET logo and FP7 wording.

## Slide 3
Actions | Target audience | Tools | Responsible | Date | Indicators | Comments
1. Maintain and update the SOLARNET website (www.solarnet-east.eu) | General public, partners, researchers, engineers, everyone involved -or interested in- SOLARNET | Web page structured in two sections, public and private. Content: information about the project (documents, reports, presentations, agenda, news, etc.) | Project Office | June 2013-March 2017 | Nr of sessions % of new sessions Avg. sessions duration Nr of page views Page/sessions Nr of countries accessing | It is expected the contribution of partners and researchers with material and information
2. Organizing schools, conferences, meetings, workshops, etc. | Scientific community | Calls, webpages, posters, presentations, brochures and other scientific and promotional material | Partners WP leaders | 2013-2017 | 4 Meetings 4 Schools 4 Workshops Other meetings | 
2.1 SOLARNER Meetings | Scientific community | Calls, web pages, mailings, brochures, etc. | UiO INAF KIS IAC | Aug 2013 Feb 2015 Sep 2015 Nov 2016 | Nr of participants Nr of presentations Meetings websites | It is expected the creation of a web page for each meeting
2.2 SOLARNET Schools and Workshops | Young researchers & postdocs | Calls, web pages, mailings, brochures, etc. | UWR AISAS IAA-CSIC QUB UCL-MSSL | Mar-Apr’14 Oct 2014 May 2015 Jan 2016 Sep 2016 | Nr of applications Nr of students Nr of lectures Schools/Workshops websites | It is expected the creation of a web page for each School/Workshop
3. Educational activities | Students, young people, general public | Talks, schools visits, meetings, brochures, posters, videos | All SOLARNET institutions | 2013-2017 | Nr. of participants Nr of talks, visits, etc. | 
3.1 Educational activities in The Canary Islands | Students, young people, general public | Canary observatories open doors days 2014, 20-21 Jun SolarLab Science weeks Infodays | IAC | 2014-2017 2013 - 2015 Yearly “ | Nr. of participants | It is expected the organization of similar activities by all SOLARNET institutions
Planning

## Slide 4
Actions | Target audience | Tools | Responsible | Date | Indicators | Comments
4. Using social networks to wider dissemination about SOLARNET project and its results | General public, partners, researchers, others | Social networks | Project Office | 2013 - 2017 | Nr of videos Nr of users Nr of tweets | 
4.1 Create and maintain the EST/SOLARNET channel in YouTube (ESTtvCHANNEL) | “ | YouTube http://www.youtube.com/user/ESTtvCHANNEL | Project Office | April 2014 | Nr of videos upload’d Nr of views | It is expected the contribution of partners and researchers
4.2 Produce 2 videos on SOLARNET activities | “ | YouTube (ESTtvCHANNEL) Other channels and means | Project Office Partners | 2015 & 2016 | Two videos produced | 1 video on TAS 1 video TBD
4.3 Create and maintain EST/SOLARNET profile in Twitter (@estsolarnet) | “ | Twitter (@estsolarnet) https://twitter.com/estsolarnet | Project Office | Jul 2014 | Nr of tweets Nr of followers Nr of retweets | 
5. Coordinate media activities with media representatives/ reporters | General public | Brochures, posters, videos, press releases to local and national media, interviews, TV and radio talks | Project Office Partners | 2014 - 2017 | Nr of brochures, press releases, radio talks, interviews, etc. | 
5.1 Create a list of media representatives and reporters to be contacted | Selected media representatives and reporters in all Europe | Post, mail, telephone | Project Office | Nov 2014 | Nr of representatives & reporters involved | It is expected the contribution of all partners
5.2 Invitation to cover workshops, events, meetings, schools, etc. | “ | Brochures, post, mail, telephone, web page, etc. | Project Office Partners | 2014 - 2017 | Nr of news and other piece of information published | 
5.3 Preparing media information and material | General public | Brochures, posters, videos, press releases, interviews, TV and radio talks | Project Office Partners | 2014 - 2017 | Nr of brochures, press releases, radio talks, interviews distributed | 
Planning (cont.)

## Slide 5
Actions | Target audience | Tools | Responsible | Date | Indicators | Comments
5.4 Schedule radio/TV appearances, interviews and announcements | General public | Radio, TV, news papers, websites, mailing | Project Office Partners | 2014 - 2017 | Nr of appearances Nr of interviews Nr of announcements | 
5.5 Organising visits to observatories, institutes and infrastructures | General public, young people, students | Radio, TV, news papers, websites, mailing | Project Office Partners | 2014 - 2017 | Nr of visits organised Nr of visitors | 
6. Dissemination of the innovative aspects and findings of the project towards industry | Selected industries, companies and organisations | Meetings, conferences, Expos, workshops, promotional technologies data sheets | Tecnalia Partners | 2014 - 2017 | Nr of technologies disseminated Nr of industries involved | It is expected the contribution of partners and researchers
7. Contacts with policy makers and funding agencies of the participants countries | Police makers, funding agencies, stakeholders, representatives, other | Meetings, interviews, brochures, posters, brief reports, videos about SOLARNET & EST | Project Office Partners | 2014 - 2017 | Mobilized funds and supports of each country to ensure the continuity of the development of EST | The implication of all partners is of paramount relevance for SOLARNET & EST
8. Outreach plan assessment | A sample of the distinct audiences | Questionnaires, web page visiting counters, etc. | Project Office Partners | 2015 & 2017 | Relevant indicators (some of them TBD) | 
Planning (cont.)

## Slide 6
Outreach activities status (up to date*)
Outreach activity | Status
Website (www.solarnet-east.eu) | Nr of sessions: 13 355 % of new sessions: 73,9 Avg. sessions duration: 1,28 min. Nr of page views: 30 244 Page/sessions: 2,26 Nr of countries: 149 ** (Analytics from 27/01/2014 to 30/09/2015)
Conferences, workshops, schools, meetings, Expos | Conferences and Meetings: 8 (Participants: 427; Presentations: 240) Schools: 3 (Participants: 78) Workshops: 3 (Participants: 116) Meetings: 3 (Participants: 275; Presentations: 194)
Educational activities (only IAC) | SolarLab: 80000 students, 300 schoolteachers, 171 participating centers Teide Observatory Open Doors Days: 5975 visitors (20-21/06/14 & 3-4/07/15)
Social networks | YouTube: EST/SOLARNET TV Channel (2 videos uploaded, 39 views) Twitter profile: Created but…
* 30/09/2015
** The countries from which visits originated, based on IP address

## Slide 7
SOLARNET Project Office
INSTITUTO DE ASTROFÍSICA DE CANARIAS
C/ Vía Láctea, s/n
38200 – La Laguna
Email: solarnet@iac.es
Tel: +34 922 605192 / 605200
Fax: +34 922 605210